## Defect_tracker
SI No | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | 2026-03-15 | Project setup issues | Sprint 1 | DevOps | Setup | Fixed environment setup | 2026-03-16 | Closed | Setup completed
2 | 2026-03-16 | IVR welcome message not working | Sprint 1 | Backend Team | Functional | Added TTS module | 2026-03-17 | Closed | Working
3 | 2026-03-18 | User input not detected correctly | Sprint 2 | Backend Team | Logic | Improved input handling | 2026-03-19 | Closed | Accurate now
4 | 2026-03-19 | Incorrect intent recognition | Sprint 2 | Backend Team | Logic | Updated intent mapping | 2026-03-20 | Closed | Fixed
5 | 2026-03-21 | IVR not responding to invalid input | Sprint 3 | Backend Team | Functional | Added fallback response | 2026-03-22 | Closed | Stable
6 | 2026-03-22 | Voice output unclear | Sprint 3 | Backend Team | UI/UX | Adjusted speech settings | 2026-03-23 | Closed | Clear voice
7 | 2026-03-24 | API response delay | Sprint 4 | Backend Team | Performance | Optimized API calls | 2026-03-25 | Closed | Faster
8 | 2026-03-25 | Server not starting | Sprint 4 | DevOps | Deployment | Fixed server config | 2026-03-25 | Closed | Running
9 | 2026-03-26 | Error under multiple users | Sprint 4 | Backend Team | Performance | Handled concurrency | 2026-03-27 | Closed | Stable